## 2022-2025 Action Plan Gantt
| 2022 | [6 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
| Q2 | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2
| JUNE | JULY | AUGOST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGOST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGOST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE
ACTIONS | Q1 MARCH: Contingency months for unfinished actions
6. Creation of a general merit model rule
11. Good practices in the performance of Selection Committees
15. Redesign of training offer for doctoral students
a) Analyse trining offer
b) up-dating and improvement training offer in English
16. Training sessions on the HRS4R Seal of Excellence
17. Analysis of UMU's strategic plans and general policies
18. Incorporating OTM-R organically at UMU
19. Opening of an e-mail box/contact form for questions about the HRS4R
20. Opening of a general channel for complaints and appeals
21. Communication plan in relation to the HR Seal within the UMU's own policies
22. Increase the number of different positions published in Euraxess
23. Training sessions on the Research Development Career
MANAGEMENT COMMITTEE (MC)
Follow up meetings MC
STEERING COMMITTEE (SC)
Control meetings | bar: Q3 JULY; Q1 JANUARY; Q3 JULY; Q1 JANUARY; Q3 JULY; Q1 JANUARY; Q2 JUNE
EXTERNAL EXPERT
Follow-up meetings | bar: Q3 SEPTEMBER; Q4 DECEMBER; Q1 MARCH; Q2 JUNE; Q3 SEPTEMBER; Q4 DECEMBER; Q1 MARCH; Q2 JUNE; Q3 SEPTEMBER; Q4 DECEMBER; Q1 MARCH; Q2 JUNE
Monitoring of actions | bar: Q1 FEBRUARY to Q2 JUNE
Researcher and stakeholder surveys | bar: Q2 JUNE; Q2 JUNE; Q1 MARCH
Internal review for site visit preparation | bar: Q1 JANUARY to Q2 JUNE